## Who_Does_What
Resources and Assignments | Start | Finish | Scheduled_Work
Aglow Canada | Tue 9/27/22 | Wed 9/28/22 | 16h
Determination and Selection of Colour specifications | Tue 9/27/22 | Wed 9/28/22 | 16h
High-Flyers Solutions Inc. | Thu 9/29/22 | Fri 12/30/22 | 584h
App Development Accounts | Thu 9/29/22 | Thu 10/27/22 | 168h
Online Database Hosting | Fri 10/28/22 | Tue 11/1/22 | 24h
Integrate Features and functionalities | Wed 11/2/22 | Thu 11/10/22 | 56h
APK File & Source code development and submission | Thu 11/10/22 | Tue 11/29/22 | 120h
APK file & hosting Andriod & IOS development account | Fri 11/25/22 | Wed 11/30/22 | 40h
Testing | Thu 12/1/22 | Fri 12/30/22 | 176h
Anderson | Sat 9/24/22 | Fri 12/30/22 | 576h
London Babysitter App WBS | Sat 9/24/22 | Fri 12/30/22 | 576h
Chika | Sat 9/24/22 | Wed 11/9/22 | 24h
Create Samples of Logo Design Templates and Presentation | Sat 9/24/22 | Mon 9/26/22 | 16h
UI/UX Interface | Wed 11/9/22 | Wed 11/9/22 | 8h
Milu | Thu 9/29/22 | Tue 11/29/22 | 80h
Create an Andriod Developer account and review policies | Thu 9/29/22 | Thu 9/29/22 | 8h
Subscribe to Firebase Cloud Databse | Fri 10/28/22 | Fri 10/28/22 | 8h
Create online version control system (GitHub) | Thu 11/10/22 | Fri 11/11/22 | 16h
Create local version control system (Andriod studio) | Mon 11/14/22 | Wed 11/16/22 | 24h
APK testing and Debugging | Sat 11/26/22 | Tue 11/29/22 | 24h
Aleena | Thu 9/29/22 | Sat 11/26/22 | 80h
Create an IOS Developer account and review policies | Thu 9/29/22 | Thu 9/29/22 | 0h
Sharing of Sign-in credentials | Thu 10/27/22 | Thu 10/27/22 | 8h
Link Database to app | Tue 11/1/22 | Tue 11/1/22 | 8h
Parent features and functions | Wed 11/2/22 | Wed 11/2/22 | 8h
Babysitter features and functions | Thu 11/3/22 | Thu 11/3/22 | 8h
Generate APK files and host both the online and local version control system | Tue 11/22/22 | Fri 11/25/22 | 32h
Host the Meta version of the London Babysitter App on Andriod and IOS | Fri 11/25/22 | Sat 11/26/22 | 16h
Soyinka | Fri 9/30/22 | Fri 12/30/22 | 256h
Subscribe to Firebase Cloud database, Set up and link to App | Fri 9/30/22 | Fri 9/30/22 | 8h
Create and host APK file and source code | Mon 10/3/22 | Wed 10/26/22 | 144h
Setting up of Firebase Cloud Database | Mon 10/31/22 | Mon 10/31/22 | 8h
Admin features and functions | Fri 11/4/22 | Sat 11/5/22 | 16h
API and 3rd Party Integrations | Mon 11/7/22 | Tue 11/8/22 | 16h
Local compilation of APK Source Codes | Thu 11/17/22 | Mon 11/21/22 | 24h
Host the full version of the London Babysitter App on Andriod and IOS after the trial period version expires in 30 days | Mon 11/28/22 | Wed 11/30/22 | 24h
Lunch application | Thu 12/29/22 | Fri 12/30/22 | 16h
Johnson | Thu 12/15/22 | Mon 12/19/22 | 24h
Usability/Performance Testing | Thu 12/15/22 | Mon 12/19/22 | 24h
Isabella | Thu 12/1/22 | Wed 12/14/22 | 80h
Software Testing and Debugging | Thu 12/1/22 | Wed 12/14/22 | 80h
Donald | Tue 12/20/22 | Wed 12/28/22 | 56h
Create Operations Manual | Tue 12/20/22 | Thu 12/22/22 | 24h
Training | Fri 12/23/22 | Wed 12/28/22 | 32h